## FinWiz_Project_Schedule
Novillex Technologies Private Ltd.
Name of Bank: |  |  | Gajanan Co-Op Bank Ltd., Beed | [12 empty] | Project Start Date | [7 empty] | 2026-06-11
Name of Project: |  |  | FinWizCBS | [12 empty] | Display week: | [7 empty] | 1
Project Manager: |  |  | Pranav Kashikar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27
 | time axis 2026-06-08 to 2026-08-02
 | time axis 2026-06-08 to 2026-08-02
1 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders |  | 0.2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.2 | 100% | Completed | On Track
2 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria |  | 0.3 | 2026-06-12 | 2026-06-15 | 2026-06-12 |  |  |  | Not Started | Delayed
3 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance |  | 0.2 | 2026-06-15 | 2026-06-15 | 2026-07-16 | 2026-07-16 | 0.2 | 100% | Completed | On Track
4 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation |  | 0.3 | 2026-06-15 | 2026-06-16 |  |  |  |  | Not Started | Delayed
5 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
6 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
7 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Define timelines milestones |  | 0.4 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
8 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Resource allocation Bank Vendor |  | 0.3 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
9 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Risk identification |  | 0.3 | 2026-06-19 | 2026-06-22 |  |  |  |  | Not Started | Delayed
10 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define reporting cadence |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
11 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Setup status templates |  | 1 | 2026-06-20 | 2026-06-25 |  |  |  |  | Not Started | Delayed
12 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define escalation reporting |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
13 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Study legacy CBS |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
14 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Identify data sources |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
15 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | History Data Migration |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
16 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Map legacy to CBS fields |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
17 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Define transformation logic |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
18 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Remove duplicates |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
19 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Correct inconsistencies |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
20 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load customer data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
21 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load account data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
22 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load Transaction data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
23 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Data Validation | Migrated Data Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
24 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Financial Report Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
25 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Exception identification |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
Formulas:
Project Start Date = [Project Start Date, row below]
Note on H5: Pranav Kashikar: Half Day : 0.1 1 Day : 0.2 2 Days : 0.4 3 Days : 0.6 1 Week : 1 2 Weeks : 2