## Sheet4
Sr. No. | Milestone | Task | Sub-Task | Activity | (empty)
1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders
(empty) | (empty) | (empty) | (empty) | (empty)
Total Result

## FinWiz_Project_Schedule
Novillex Technologies Pvt Ltd.
Name of Bank: |  |  | Shri Chhatrapati Rajarshi Shahu Urban Co-Op Bank Ltd., Beed
Name of Project: |  |  | FinWiz CBS
Project Manager: |  |  | Pranav Kashikar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | Remark
1 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders |  | 0.2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.2 | 100% | Completed | On Track
2 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria |  | 0.3 | 2026-06-12 | 2026-06-15 | 2026-06-12 | 2026-06-12 | 0.2 | 100% | Completed | On Track | Add remark Add define
3 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance |  | 0.2 | 2026-06-15 | 2026-06-15 |  |  |  |  | Not Started | Delayed
Formulas:
Actual Period (in week) = IF(OR(ISBLANK([Actual Start Date]),ISBLANK([Actual End Date])),"",NETWORKDAYS([Actual Start Date],[Actual End Date])/5)
Schedule Health = IF([Progress]>=1, IF([Actual Period (in week)]>[Actual Start Date],"Delayed","On Track"), IF(TODAY()<[Planned End Date], "On Track", IF(AND([Progress]=0,TODAY()>[Actual Start Date]), "Delayed", IF(AND([Actual End Date]<>"",[Actual End Date]>[Planned End Date]), "At Risk", IF(TODAY()>[Actual Start Date], "Delayed", "On Track")))))

## Sheet1
Font | Cambria
| Chart/Graph | Requirement
| Task wise Bar chart | Planned vs Achieved
| Task wise Doughnut chart | Doughnut Graft with Percentage
| Phase Wise Bar Chart | Planned vs Achieved
| Phase wise Doughnut chart | Doughnut Graft with Percentage
| Overall Bar chart | Planned vs Achieved
| Overall Doughnut chart | Doughnut Graft with Percentage