## Sheet4
Sr. No. | Milestone | Task | Sub-Task | Activity | (empty)
1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders
(empty) | (empty) | (empty) | (empty) | (empty)
Total Result

## FinWiz_Project_Schedule
Novillex Technologies Pvt Ltd.
Name of Bank: |  |  | ABC Co-Op Bank Ltd., Beed (ABC Bank)
Name of Project: |  |  | FinWiz_CBS
Project Manager: |  |  | Pranav Kashikar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | Remark
1 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders |  | 0.2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.2 | 100% | Completed | On Track
2 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria |  | 0.3 | 2026-06-12 | 2026-06-15 | 2026-06-12 | 2026-06-12 | 0.2 | 100% | Completed | On Track
3 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance |  | 0.2 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 0.2 | 100% | Completed | On Track
4 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation |  | 0.3 | 2026-06-15 | 2026-06-16 | 2026-07-15 | 2026-07-16 | 0.4 | 100% | Completed | On Track
5 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
6 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
7 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Define timelines milestones |  | 0.4 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
8 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Resource allocation Bank Vendor |  | 0.3 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
9 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Risk identification |  | 0.3 | 2026-06-19 | 2026-06-22 |  |  |  |  | Not Started | Delayed
10 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define reporting cadence |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
11 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Setup status templates |  | 1 | 2026-06-20 | 2026-06-25 |  |  |  |  | Not Started | Delayed
12 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define escalation reporting |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
13 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Study legacy CBS |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
14 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Identify data sources |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
15 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | History Data Migration |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
16 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Map legacy to CBS fields |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
17 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Define transformation logic |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
18 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Remove duplicates |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
19 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Correct inconsistencies |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
20 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load customer data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
21 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load account data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
22 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load Transaction data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
23 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Data Validation | Migrated Data Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
24 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Financial Report Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
25 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Exception identification |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
26 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Requirement Workshops | Core Modules | Core Module List* |  | 2 | 2026-06-22 | 2026-07-03 |  |  |  |  | Not Started | Delayed
27 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Requirement Workshops | Digital Channels | Digital Channel Module List* |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
28 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | NPCI Rails | UPI IMPS NACH AEPS NFS BBPS FASTag |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
29 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | RBI Systems | NEFT RTGS |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
30 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Government Systems | PFMS DBT CBDT |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
31 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Mandate | eNACH registration debit lifecycle |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
32 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Switch & Channels | ATM POS UPI IMPS routing |  | 1 | 2026-07-13 | 2026-07-17 |  |  |  |  | Not Started | Delayed
33 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Gap Analysis | Gap Identification | Identify gaps |  | 1 | 2026-07-13 | 2026-07-17 |  |  |  |  | Not Started | Delayed
34 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Gap Analysis | Gap Prioritization | Categorize gaps |  | 0.4 | 2026-07-17 | 2026-07-20 |  |  |  |  | Not Started | Delayed
35 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Sign-off | Approval | Requirement gap sign-off |  | 0.4 | 2026-07-21 | 2026-07-22 |  |  |  |  | Not Started | Delayed
36 | Phase-1 | M04 - Solution Design & Configuration | Solution Design | Architecture Design | CBS architecture |  | 0.4 | 2026-07-23 | 2026-07-24 |  |  |  |  | Not Started | Delayed
37 | Phase-1 | M04 - Solution Design & Configuration | Solution Design | Architecture Design | Integration architecture (third party vendor) |  | 0.4 | 2026-07-27 | 2026-07-28 |  |  |  |  | Not Started | On Track
38 | Phase-1 | M04 - Solution Design & Configuration | Product Configuration | Setup | Product Checklist* |  | 0.8 | 2026-07-29 | 2026-08-03 |  |  |  |  | Not Started | On Track
39 | Phase-1 | M04 - Solution Design & Configuration | Accounting Setup | GL Product Setup | GL mapping interest charges* |  | 0.2 | 2026-08-04 | 2026-08-04 |  |  |  |  | Not Started | On Track
40 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | NPCI Design | API file structure sponsor bank |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
41 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | RBI Design | NEFT RTGS design |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
42 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | Switch Design | ATM POS UPI IMPS routing |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
43 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | Government Design | PFMS DBT flows |  | 0.2 | 2026-08-10 | 2026-08-10 |  |  |  |  | Not Started | On Track
44 | Phase-1 | M04 - Solution Design & Configuration | Settlement Design | Reconciliation | Settlement flows reconciliation |  | 0.4 | 2026-08-10 | 2026-08-11 |  |  |  |  | Not Started | On Track
45 | Phase-1 | M04 - Solution Design & Configuration | Mandate Design | Lifecycle | Registration execution cancellation |  | 0.4 | 2026-08-12 | 2026-08-13 |  |  |  |  | Not Started | On Track
46 | Phase-1 | M05 - Development & Gap Closure | Core Development | Gap Development | Critical high gaps |  | 3 | 2026-07-22 | 2026-08-11 |  |  |  |  | Not Started | On Track
47 | Phase-1 | M05 - Development & Gap Closure | Integration Development | NPCI | UPI IMPS NACH AEPS |  | 1 | 2026-08-14 | 2026-08-20 |  |  |  |  | Not Started | On Track
48 | Phase-1 | M05 - Development & Gap Closure | Integration Development | RBI | NEFT RTGS |  | 2 | 2026-08-14 | 2026-08-27 |  |  |  |  | Not Started | On Track
49 | Phase-1 | M05 - Development & Gap Closure | Integration Development | Switch | ATM POS UPI IMPS |  | 4 | 2026-08-08 | 2026-09-03 |  |  |  |  | Not Started | On Track
50 | Phase-1 | M05 - Development & Gap Closure | Integration Development | Government | PFMS DBT CBDT |  | 1 | 2026-08-08 | 2026-08-13 |  |  |  |  | Not Started | On Track
51 | Phase-1 | M05 - Development & Gap Closure | Mandate Engine | Development | Registration validation execution |  | 0.4 | 2026-08-14 | 2026-08-17 |  |  |  |  | Not Started | On Track
Formulas:
Actual Period (in week) = IF(OR(ISBLANK([Actual Start Date]),ISBLANK([Actual End Date])),"",NETWORKDAYS([Actual Start Date],[Actual End Date])/5)
Schedule Health = IF([Progress]>=1, IF([Actual Period (in week)]>[Actual Start Date],"Delayed","On Track"), IF(TODAY()<[Planned End Date], "On Track", IF(AND([Progress]=0,TODAY()>[Actual Start Date]), "Delayed", IF(AND([Actual End Date]<>"",[Actual End Date]>[Planned End Date]), "At Risk", IF(TODAY()>[Actual Start Date], "Delayed", "On Track")))))

## Sheet1
Font | Cambria
| Chart/Graph | Requirement
| Task wise Bar chart | Planned vs Achieved
| Task wise Doughnut chart | Doughnut Graft with Percentage
| Phase Wise Bar Chart | Planned vs Achieved
| Phase wise Doughnut chart | Doughnut Graft with Percentage
| Overall Bar chart | Planned vs Achieved
| Overall Doughnut chart | Doughnut Graft with Percentage