## FinWiz_Project_Schedule
Novillex Technologies Private Ltd.
Name of Bank: |  |  | Shri Chhatrapati Rajarshi Shahu Urban Co-Op Bank Ltd., Beed | [12 empty] | Project Start Date | [7 empty] | 2026-06-11
Name of Project: |  |  | FinWiz CBS | [12 empty] | Display week: | [7 empty] | 1
Project Manager: |  |  | Pranav Kashikar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27
 | time axis 2026-06-08 to 2026-08-02
 | time axis 2026-06-08 to 2026-08-02
1 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation |  | 0.3 | 2026-06-15 | 2026-06-16 |  |  |  |  | Not Started | Delayed
2 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
3 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
Formulas:
Display week: = [Display week:, row below]
Note on H5: Pranav Kashikar: Half Day : 0.1 1 Day : 0.2 2 Days : 0.4 3 Days : 0.6 1 Week : 1 2 Weeks : 2