## FinWiz_Project_Schedule
Novillex Technologies Private Ltd.
Name of Bank: |  |  | Shri Chhatrapati Rajarshi Shahu Urban Co-Op Bank Ltd., Beed | [12 empty] | Project Start Date | [7 empty] | 2026-06-11
Name of Project: |  |  | FinWiz CBS | [12 empty] | Display week: | [7 empty] | 1
Project Manager: |  |  | Pranav Kashikar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27
 | time axis 2026-06-08 to 2026-08-02
 | time axis 2026-06-08 to 2026-08-02
1 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders |  | 0.2 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 0.2 | 100% | Completed | On Track
2 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria |  | 0.3 | 2026-06-12 | 2026-06-15 | 2026-06-12 | 2026-06-12 | 0.2 | 100% | Completed | On Track
3 | Phase-1 | M01 - Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance |  | 0.2 | 2026-06-15 | 2026-06-15 |  |  |  |  | Not Started | Delayed
4 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation |  | 0.3 | 2026-06-15 | 2026-06-16 |  |  |  |  | Not Started | Delayed
5 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
6 | Phase-1 | M01 - Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy |  | 0.2 | 2026-06-17 | 2026-06-17 |  |  |  |  | Not Started | Delayed
7 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Define timelines milestones |  | 0.4 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
8 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Resource allocation Bank Vendor |  | 0.3 | 2026-06-18 | 2026-06-19 |  |  |  |  | Not Started | Delayed
9 | Phase-1 | M01 - Project Initiation & Governance | Project Planning | Implementation Planning | Risk identification |  | 0.3 | 2026-06-19 | 2026-06-22 |  |  |  |  | Not Started | Delayed
10 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define reporting cadence |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
11 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Setup status templates |  | 1 | 2026-06-20 | 2026-06-25 |  |  |  |  | Not Started | Delayed
12 | Phase-1 | M01 - Project Initiation & Governance | Communication Setup | Reporting Framework | Define escalation reporting |  | 0.2 | 2026-06-20 | 2026-06-20 |  |  |  |  | Not Started | Delayed
13 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Study legacy CBS |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
14 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | Identify data sources |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
15 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Understanding | Source Analysis | History Data Migration |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
16 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Map legacy to CBS fields |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
17 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Define transformation logic |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
18 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Remove duplicates |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
19 | Phase-1 | M02 - Data Migration – Iteration 1 | Data Cleansing | Data Quality | Correct inconsistencies |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
20 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load customer data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
21 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load account data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
22 | Phase-1 | M02 - Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load Transaction data |  | 3 | 2026-06-15 | 2026-07-03 |  |  |  |  | Not Started | Delayed
23 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Data Validation | Migrated Data Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
24 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Financial Report Validation* |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
25 | Phase-1 | M02 - Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Exception identification |  | 2 | 2026-06-29 | 2026-07-10 |  |  |  |  | Not Started | Delayed
26 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Requirement Workshops | Core Modules | Core Module List* |  | 2 | 2026-06-22 | 2026-07-03 |  |  |  |  | Not Started | Delayed
27 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Requirement Workshops | Digital Channels | Digital Channel Module List* |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
28 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | NPCI Rails | UPI IMPS NACH AEPS NFS BBPS FASTag |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
29 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | RBI Systems | NEFT RTGS |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
30 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Government Systems | PFMS DBT CBDT |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
31 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Mandate | eNACH registration debit lifecycle |  | 1 | 2026-07-06 | 2026-07-10 |  |  |  |  | Not Started | Delayed
32 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Integration Requirements | Switch & Channels | ATM POS UPI IMPS routing |  | 1 | 2026-07-13 | 2026-07-17 |  |  |  |  | Not Started | On Track
33 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Gap Analysis | Gap Identification | Identify gaps |  | 1 | 2026-07-13 | 2026-07-17 |  |  |  |  | Not Started | On Track
34 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Gap Analysis | Gap Prioritization | Categorize gaps |  | 0.4 | 2026-07-17 | 2026-07-20 |  |  |  |  | Not Started | On Track
35 | Phase-1 | M03 - Requirement Validation & Gap Analysis | Sign-off | Approval | Requirement gap sign-off |  | 0.4 | 2026-07-21 | 2026-07-22 |  |  |  |  | Not Started | On Track
36 | Phase-1 | M04 - Solution Design & Configuration | Solution Design | Architecture Design | CBS architecture |  | 0.4 | 2026-07-23 | 2026-07-24 |  |  |  |  | Not Started | On Track
37 | Phase-1 | M04 - Solution Design & Configuration | Solution Design | Architecture Design | Integration architecture (third party vendor) |  | 0.4 | 2026-07-27 | 2026-07-28 |  |  |  |  | Not Started | On Track
38 | Phase-1 | M04 - Solution Design & Configuration | Product Configuration | Setup | Product Checklist* |  | 0.8 | 2026-07-29 | 2026-08-03 |  |  |  |  | Not Started | On Track
39 | Phase-1 | M04 - Solution Design & Configuration | Accounting Setup | GL Product Setup | GL mapping interest charges* |  | 0.2 | 2026-08-04 | 2026-08-04 |  |  |  |  | Not Started | On Track
40 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | NPCI Design | API file structure sponsor bank |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
41 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | RBI Design | NEFT RTGS design |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
42 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | Switch Design | ATM POS UPI IMPS routing |  | 0.6 | 2026-08-05 | 2026-08-07 |  |  |  |  | Not Started | On Track
43 | Phase-1 | M04 - Solution Design & Configuration | Integration Design | Government Design | PFMS DBT flows |  | 0.2 | 2026-08-10 | 2026-08-10 |  |  |  |  | Not Started | On Track
44 | Phase-1 | M04 - Solution Design & Configuration | Settlement Design | Reconciliation | Settlement flows reconciliation |  | 0.4 | 2026-08-10 | 2026-08-11 |  |  |  |  | Not Started | On Track
45 | Phase-1 | M04 - Solution Design & Configuration | Mandate Design | Lifecycle | Registration execution cancellation |  | 0.4 | 2026-08-12 | 2026-08-13 |  |  |  |  | Not Started | On Track
46 | Phase-1 | M05 - Development & Gap Closure | Core Development | Gap Development | Critical high gaps |  | 3 | 2026-07-22 | 2026-08-11 |  |  |  |  | Not Started | On Track
47 | Phase-1 | M05 - Development & Gap Closure | Integration Development | NPCI | UPI IMPS NACH AEPS |  | 1 | 2026-08-14 | 2026-08-20 |  |  |  |  | Not Started | On Track
48 | Phase-1 | M05 - Development & Gap Closure | Integration Development | RBI | NEFT RTGS |  | 2 | 2026-08-14 | 2026-08-27 |  |  |  |  | Not Started | On Track
49 | Phase-1 | M05 - Development & Gap Closure | Integration Development | Switch | ATM POS UPI IMPS |  | 4 | 2026-08-08 | 2026-09-03 |  |  |  |  | Not Started | On Track
50 | Phase-1 | M05 - Development & Gap Closure | Integration Development | Government | PFMS DBT CBDT |  | 1 | 2026-08-08 | 2026-08-13 |  |  |  |  | Not Started | On Track
51 | Phase-1 | M05 - Development & Gap Closure | Mandate Engine | Development | Registration validation execution |  | 0.4 | 2026-08-14 | 2026-08-17 |  |  |  |  | Not Started | On Track
52 | Phase-1 | M06 - Testing (QA + SIT) | Test Planning | Strategy | Test strategy test cases |  | 0.6 | 2026-08-08 | 2026-08-11 |  |  |  |  | Not Started | On Track
53 | Phase-1 | M06 - Testing (QA + SIT) | Functional Testing | CBS | Core Module + Functionalities List* |  | 0.6 | 2026-08-12 | 2026-08-14 |  |  |  |  | Not Started | On Track
54 | Phase-1 | M06 - Testing (QA + SIT) | Integration Testing | NPCI | UPI IMPS NACH |  | 0.6 | 2026-08-21 | 2026-08-25 |  |  |  |  | Not Started | On Track
55 | Phase-1 | M06 - Testing (QA + SIT) | Integration Testing | RBI | NEFT RTGS |  | 1 | 2026-08-21 | 2026-08-27 |  |  |  |  | Not Started | On Track
56 | Phase-1 | M06 - Testing (QA + SIT) | Integration Testing | Switch | ATM POS |  | 1 | 2026-08-21 | 2026-08-27 |  |  |  |  | Not Started | On Track
57 | Phase-1 | M06 - Testing (QA + SIT) | Integration Testing | Third Party Vendor | Third Party Vendor |  | 1 | 2026-08-21 | 2026-08-27 |  |  |  |  | Not Started | On Track
58 | Phase-1 | M06 - Testing (QA + SIT) | Settlement Testing | Validation | Settlement GL Transactions |  | 0.4 | 2026-08-28 | 2026-08-31 |  |  |  |  | Not Started | On Track
59 | Phase-1 | M06 - Testing (QA + SIT) | Failure Testing | Scenarios | Timeout reversal duplicate |  | 1 | 2026-08-28 | 2026-09-03 |  |  |  |  | Not Started | On Track
60 | Phase-1 | M07 - Training | Training Preparation | Material | Training materials SOP |  | 1 | 2026-08-28 | 2026-09-03 |  |  |  |  | Not Started | On Track
61 | Phase-1 | M07 - Training | Training Execution | Technical | IT admin |  | 0.4 | 2026-09-04 | 2026-09-07 |  |  |  |  | Not Started | On Track
62 | Phase-1 | M07 - Training | Training Execution | Users | Branch operations |  | 1.2 | 2026-09-08 | 2026-09-15 |  |  |  |  | Not Started | On Track
63 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Planning | Scenarios | Define scope users |  | 0.4 | 2026-09-14 | 2026-09-15 |  |  |  |  | Not Started | On Track
64 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Core Banking | Core Module + Functionalities List* |  | 3 | 2026-09-16 | 2026-10-06 |  |  |  |  | Not Started | On Track
65 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Channels | Digital Channel Module List* |  | 3 | 2026-09-16 | 2026-10-06 |  |  |  |  | Not Started | On Track
66 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Payments | UPI IMPS NACH NEFT RTGS AEPS CTS |  | 1 | 2026-09-16 | 2026-09-22 |  |  |  |  | Not Started | On Track
67 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Government | PFMS DBT |  | 0.4 | 2026-09-16 | 2026-09-17 |  |  |  |  | Not Started | On Track
68 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Mandate | Registration execution |  | 0.4 | 2026-09-16 | 2026-09-17 |  |  |  |  | Not Started | On Track
69 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Settlement | GL reconciliation exception |  | 1 | 2026-09-16 | 2026-09-22 |  |  |  |  | Not Started | On Track
70 | Phase-1 | M08 - UAT- 1 (Bank Level) | UAT Execution | Reporting | Regulatory MIS* |  | 3 | 2026-09-16 | 2026-10-06 |  |  |  |  | Not Started | On Track
71 | Phase-1 | M08 - UAT- 1 (Bank Level) | Issue Resolution | Fixes | Resolve defects revalidation |  | 3 | 2026-09-16 | 2026-10-06 |  |  |  |  | Not Started | On Track
72 | Phase-1 | M08 - UAT- 1 (Bank Level) | Sign-off | Approval | Branch Ops Finance IT final |  | 0.6 | 2026-10-07 | 2026-10-09 |  |  |  |  | Not Started | On Track
73 | Phase-1 | M09 - Data Migration – Iteration 2 | Migration | Execution | Reload corrected data |  | 0.6 | 2026-10-07 | 2026-10-09 |  |  |  |  | Not Started | On Track
74 | Phase-1 | M09 - Data Migration – Iteration 2 | Validation | Final | Reconciliation |  | 0.6 | 2026-10-09 | 2026-10-13 |  |  |  |  | Not Started | On Track
75 | Phase-1 | M10 - UAT- 2 (High Level) | Execution | End to End | Full system validation |  | 0.8 | 2026-10-14 | 2026-10-19 |  |  |  |  | Not Started | On Track
76 | Phase-1 | M10 - UAT- 2 (High Level) | Reporting | Validation | MIS regulatory |  | 0.8 | 2026-10-14 | 2026-10-19 |  |  |  |  | Not Started | On Track
77 | Phase-1 | M10 - UAT- 2 (High Level) | Reporting | Validation | One Day Voucher Posting |  | 0.4 | 2026-10-20 | 2026-10-21 |  |  |  |  | Not Started | On Track
78 | Phase-1 | M10 - UAT- 2 (High Level) | Sign-off | Final | Business approval |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
79 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Technical | Infra readiness |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
80 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Data | Migration approval |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
81 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Application | System validation |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
82 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Integration | NPCI RBI Switch validation |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
83 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Business | User readiness |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
84 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Compliance | Regulatory validation |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
85 | Phase-1 | M11 - Go-Live Readiness & Sign-Off | Sign-off | Final | Go-live approval |  | 0.4 | 2026-10-22 | 2026-10-23 |  |  |  |  | Not Started | On Track
86 | Phase-1 | M12 - Go-Live | Migration | Data Copy | Data Backup & Copy from Bank Environment |  | 0.2 | 2026-11-13 | 2026-11-13 |  |  |  |  | Not Started | On Track
87 | Phase-1 | M12 - Go-Live | Migration | Data Transfer | Data transfer from Bank to Data Center |  | 0.2 | 2026-11-13 | 2026-11-13 |  |  |  |  | Not Started | On Track
88 | Phase-1 | M12 - Go-Live | Migration | Execution | Final Migration |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
89 | Phase-1 | M12 - Go-Live | Migration | Validation | Reconciliation |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
90 | Phase-1 | M12 - Go-Live | Migration | Final | Production Data Restore |  | 0.2 | 2026-11-15 | 2026-11-15 |  |  |  |  | Not Started | On Track
91 | Phase-1 | M12 - Go-Live | Reporting | Validation | MIS |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
92 | Phase-1 | M12 - Go-Live | Sign-off | Final | Business approval |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
93 | Phase-1 | M12 - Go-Live | Sign-off | Final | Go-live approval |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
94 | Phase-1 | M12 - Go-Live | Sign-off | Technical | Infra readiness |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
95 | Phase-1 | M12 - Go-Live | Sign-off | Data | Migration approval |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
96 | Phase-1 | M12 - Go-Live | Sign-off | Application | System validation |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
97 | Phase-1 | M12 - Go-Live | Sign-off | Integration | NPCI RBI Switch validation |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
98 | Phase-1 | M12 - Go-Live | Sign-off | Business | User readiness |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
99 | Phase-1 | M12 - Go-Live | Sign-off | Compliance | Regulatory validation |  | 0.2 | 2026-11-14 | 2026-11-14 |  |  |  |  | Not Started | On Track
100 | Phase-1 | M12 - Go-Live | Activation | CBS | Enable accounts transactions |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
101 | Phase-1 | M12 - Go-Live | Activation | NPCI | UPI IMPS NACH AEPS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
102 | Phase-1 | M12 - Go-Live | Activation | RBI | NEFT RTGS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
103 | Phase-1 | M12 - Go-Live | Activation | Switch | ATM POS UPI IMPS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
104 | Phase-1 | M12 - Go-Live | Activation | Government | PFMS DBT |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
105 | Phase-1 | M12 - Go-Live | Activation | Channels | Mobile Internet APIs |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
106 | Phase-1 | M12 - Go-Live | Monitoring | Transactions | Validate transactions |  | 0.6 | 2026-11-16 | 2026-11-18 |  |  |  |  | Not Started | On Track
107 | Phase-1 | M12 - Go-Live | Support | Issue Handling | Resolve issues |  | 0.8 | 2026-11-16 | 2026-11-19 |  |  |  |  | Not Started | On Track
108 | Phase-1 | M13 - Post Go-Live Stabilization | Hypercare | Support | Onsite support |  | 1.5 | 2026-11-17 | 2026-11-26 |  |  |  |  | Not Started | On Track
109 | Phase-1 | M13 - Post Go-Live Stabilization | Monitoring | Performance | System monitoring |  | 1.2 | 2026-11-17 | 2026-11-24 |  |  |  |  | Not Started | On Track
110 | Phase-1 | M13 - Post Go-Live Stabilization | Resolution | Fixes | Bug fixing |  | 1.2 | 2026-11-18 | 2026-11-25 |  |  |  |  | Not Started | On Track
111 | Phase-1 | M13 - Post Go-Live Stabilization | Closure | Documentation | Closure lessons learned |  | 0.6 | 2026-11-25 | 2026-11-27 |  |  |  |  | Not Started | On Track
Formulas:
Display week: = [Display week:, row below]
Note on H5: Pranav Kashikar: Half Day : 0.1 1 Day : 0.2 2 Days : 0.4 3 Days : 0.6 1 Week : 1 2 Weeks : 2