## Sheet4
Sr. No. | Milestone | Task | Sub-Task | Activity
1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders
2 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria
3 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance
4 | Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation
5 | Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix
6 | Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy
7 | Project Initiation & Governance | Project Planning | Implementation Planning | Define timelines milestones
8 | Project Initiation & Governance | Project Planning | Implementation Planning | Resource allocation Bank Vendor
9 | Project Initiation & Governance | Project Planning | Implementation Planning | Risk identification
10 | Project Initiation & Governance | Communication Setup | Reporting Framework | Define reporting cadence
11 | Project Initiation & Governance | Communication Setup | Reporting Framework | Setup status templates
12 | Project Initiation & Governance | Communication Setup | Reporting Framework | Define escalation reporting
13 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | Study legacy CBS
14 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | Identify data sources
15 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | History Data Migration
16 | Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Map legacy to CBS fields
17 | Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Define transformation logic
18 | Data Migration – Iteration 1 | Data Cleansing | Data Quality | Remove duplicates
19 | Data Migration – Iteration 1 | Data Cleansing | Data Quality | Correct inconsistencies
20 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load customer data
21 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load account data
22 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load Transaction data
23 | Data Migration – Iteration 1 | Validation & Reconciliation | Data Validation | Migrated Data Validation*
24 | Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Financial Report Validation*
25 | Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Exception identification
26 | Requirement Validation & Gap Analysis | Requirement Workshops | Core Modules | Core Module List*
27 | Requirement Validation & Gap Analysis | Requirement Workshops | Digital Channels | Digital Channel Module List*
28 | Requirement Validation & Gap Analysis | Integration Requirements | NPCI Rails | UPI IMPS NACH AEPS NFS BBPS FASTag
29 | Requirement Validation & Gap Analysis | Integration Requirements | RBI Systems | NEFT RTGS
30 | Requirement Validation & Gap Analysis | Integration Requirements | Government Systems | PFMS DBT CBDT
31 | Requirement Validation & Gap Analysis | Integration Requirements | Switch & Channels | ATM POS UPI IMPS routing
32 | Requirement Validation & Gap Analysis | Integration Requirements | Mandate | eNACH registration debit lifecycle
33 | Requirement Validation & Gap Analysis | Gap Analysis | Gap Identification | Identify gaps
34 | Requirement Validation & Gap Analysis | Gap Analysis | Gap Prioritization | Categorize gaps
35 | Requirement Validation & Gap Analysis | Sign-off | Approval | Requirement gap sign-off
36 | Solution Design & Configuration | Solution Design | Architecture Design | CBS architecture
37 | Solution Design & Configuration | Solution Design | Architecture Design | Integration architecture (third party vendor)
38 | Solution Design & Configuration | Product Configuration | Setup | Product Checklist*
39 | Solution Design & Configuration | Accounting Setup | GL Product Setup | GL mapping interest charges*
40 | Solution Design & Configuration | Integration Design | NPCI Design | API file structure sponsor bank
41 | Solution Design & Configuration | Integration Design | RBI Design | NEFT RTGS design
42 | Solution Design & Configuration | Integration Design | Switch Design | ATM POS UPI IMPS routing
43 | Solution Design & Configuration | Integration Design | Government Design | PFMS DBT flows
44 | Solution Design & Configuration | Settlement Design | Reconciliation | Settlement flows reconciliation
45 | Solution Design & Configuration | Mandate Design | Lifecycle | Registration execution cancellation
46 | Development & Gap Closure | Core Development | Gap Development | Critical high gaps
47 | Development & Gap Closure | Integration Development | NPCI | UPI IMPS NACH AEPS
48 | Development & Gap Closure | Integration Development | RBI | NEFT RTGS
49 | Development & Gap Closure | Integration Development | Switch | ATM POS UPI IMPS
50 | Development & Gap Closure | Integration Development | Government | PFMS DBT CBDT
51 | Development & Gap Closure | Mandate Engine | Development | Registration validation execution
52 | Testing (QA + SIT) | Test Planning | Strategy | Test strategy test cases
53 | Testing (QA + SIT) | Functional Testing | CBS | Core Module + Functionalities List*
54 | Testing (QA + SIT) | Integration Testing | NPCI | UPI IMPS NACH
55 | Testing (QA + SIT) | Integration Testing | RBI | NEFT RTGS
56 | Testing (QA + SIT) | Integration Testing | Switch | ATM POS
57 | Testing (QA + SIT) | Integration Testing | Third Party Vendor | Third Party Vendor
|  | Settlement Testing | Validation | Settlement GL Transactions
58 | Testing (QA + SIT) | Failure Testing | Scenarios | Timeout reversal duplicate
59 | Training | Training Preparation | Material | Training materials SOP
60 | Training | Training Execution | Users | Branch operations
61 | Training | Training Execution | Technical | IT admin
62 | UAT- 1 (Bank Level) | UAT Planning | Scenarios | Define scope users
63 | UAT- 1 (Bank Level) | UAT Execution | Core Banking | Core Module + Functionalities List*
64 | UAT- 1 (Bank Level) | UAT Execution | Channels | Digital Channel Module List*
65 | UAT- 1 (Bank Level) | UAT Execution | Payments | UPI IMPS NACH NEFT RTGS AEPS CTS
66 | UAT- 1 (Bank Level) | UAT Execution | Government | PFMS DBT
67 | UAT- 1 (Bank Level) | UAT Execution | Mandate | Registration execution
68 | UAT- 1 (Bank Level) | UAT Execution | Settlement | GL reconciliation exception
69 | UAT- 1 (Bank Level) | UAT Execution | Reporting | Regulatory MIS*
70 | UAT- 1 (Bank Level) | Issue Resolution | Fixes | Resolve defects revalidation
71 | UAT- 1 (Bank Level) | Sign-off | Approval | Branch Ops Finance IT final
72 | Data Migration – Iteration 2 | Migration | Execution | Reload corrected data
73 | Data Migration – Iteration 2 | Validation | Final | Reconciliation
74 | UAT- 2 (High Level) | Execution | End to End | Full system validation
75 | UAT- 2 (High Level) | Reporting | Validation | MIS regulatory
76 | UAT- 2 (High Level) | Reporting | Validation | One Day Voucher Posting
|  | Sign-off | Final | Business approval
77 | Go-Live Readiness & Sign-Off | Sign-off | Technical | Infra readiness
78 | Go-Live Readiness & Sign-Off | Sign-off | Data | Migration approval
79 | Go-Live Readiness & Sign-Off | Sign-off | Application | System validation
80 | Go-Live Readiness & Sign-Off | Sign-off | Integration | NPCI RBI Switch validation
81 | Go-Live Readiness & Sign-Off | Sign-off | Business | User readiness
82 | Go-Live Readiness & Sign-Off | Sign-off | Compliance | Regulatory validation
83 | Go-Live Readiness & Sign-Off | Sign-off | Final | Go-live approval
84 | Go-Live | Migration | Final | Production Data Restore
85 | Go-Live | Activation | CBS | Enable accounts transactions
86 | Go-Live | Activation | NPCI | UPI IMPS NACH AEPS
87 | Go-Live | Activation | RBI | NEFT RTGS
88 | Go-Live | Activation | Switch | ATM POS UPI IMPS
89 | Go-Live | Activation | Government | PFMS DBT
90 | Go-Live | Activation | Channels | Mobile Internet APIs
91 | Go-Live | Monitoring | Transactions | Validate transactions
92 | Go-Live | Support | Issue Handling | Resolve issues
93 | Post Go-Live Stabilization | Hypercare | Support | Onsite support
94 | Post Go-Live Stabilization | Monitoring | Performance | System monitoring
95 | Post Go-Live Stabilization | Resolution | Fixes | Bug fixing
96 | Post Go-Live Stabilization | Closure | Documentation | Closure lessons learned
(blank) | (blank) | (blank) | (blank) | (blank)

## Project schedule
Novillex Technologies Pvt Ltd.
Name of Bank: |  |  | Deogiri Nagari Sahakari Bank Ltd., | [12 empty] | Project Start Date | [7 empty] | 2026-04-16
Name of Project: |  |  | Deogiri Sarathi | [12 empty] | Display week: | [7 empty] | 5
Project Manager: |  |  | Manoj Kulkarni / Pranav Kashilkar
Sr. No. | Phase | Milestone | Task | Sub-Task | Activity | Owner | Estimated Period (in week) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Actual Period (in week) | Progress | Execution Status | Schedule Health | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29
 | time axis 2026-05-11 to 2026-07-05
 | time axis 2026-05-11 to 2026-07-05
1 | Phase-1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Introduce stakeholders |  | 0.2 | 2026-04-15 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 0.2 | 100% | Completed | On Track
2 | Phase-1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Define scope objectives success criteria |  | 0.3 | 2026-04-15 | 2026-04-17 | 2026-04-16 | 2026-04-17 | 0.4 | 80% | In Progress | Delayed
3 | Phase-1 | Project Initiation & Governance | Project Kickoff | Kickoff Meeting | Identify stakeholders Business IT Ops Finance |  | 0.2 | 2026-04-16 | 2026-04-17 | 2026-04-22 | 2026-04-24 | 0.6 | 100% | Completed | On Track
4 | Phase-1 | Project Initiation & Governance | Governance Setup | Governance Model | Steering committee formation |  | 0.3 | 2026-04-16 | 2026-04-18 | 2026-04-18 |  |  |  | Not Started | Delayed
5 | Phase-1 | Project Initiation & Governance | Governance Setup | Governance Model | Define escalation matrix |  | 0.2 | 2026-04-17 | 2026-04-18 |  |  |  |  | Not Started | Delayed
6 | Phase-1 | Project Initiation & Governance | Governance Setup | Governance Model | Define approval hierarchy |  | 0.2 | 2026-04-17 | 2026-04-18 |  |  |  |  | Not Started | Delayed
7 | Phase-1 | Project Initiation & Governance | Project Planning | Implementation Planning | Define timelines milestones |  | 0.3 | 2026-04-18 | 2026-04-21 |  |  |  |  | Not Started | Delayed
8 | Phase-1 | Project Initiation & Governance | Project Planning | Implementation Planning | Resource allocation Bank Vendor |  | 0.3 | 2026-04-18 | 2026-04-21 |  |  |  |  | Not Started | Delayed
9 | Phase-1 | Project Initiation & Governance | Project Planning | Implementation Planning | Risk identification |  | 0.2 | 2026-04-19 | 2026-04-21 |  |  |  |  | Not Started | Delayed
10 | Phase-1 | Project Initiation & Governance | Communication Setup | Reporting Framework | Define reporting cadence |  | 0.2 | 2026-04-20 | 2026-04-22 |  |  |  |  | Not Started | Delayed
11 | Phase-1 | Project Initiation & Governance | Communication Setup | Reporting Framework | Setup status templates |  | 0.2 | 2026-04-20 | 2026-04-22 |  |  |  |  | Not Started | Delayed
12 | Phase-1 | Project Initiation & Governance | Communication Setup | Reporting Framework | Define escalation reporting |  | 0.2 | 2026-04-21 | 2026-04-22 |  |  |  |  | Not Started | Delayed
13 | Phase-1 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | Study legacy CBS |  | 0.6 | 2026-04-20 | 2026-04-25 |  |  |  |  | Not Started | Delayed
14 | Phase-1 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | Identify data sources |  | 0.5 | 2026-04-21 | 2026-04-25 |  |  |  |  | Not Started | Delayed
15 | Phase-1 | Data Migration – Iteration 1 | Data Understanding | Source Analysis | History Data Migration |  | 0.8 | 2026-04-26 | 2026-05-02 |  |  |  |  | Not Started | Delayed
16 | Phase-1 | Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Map legacy to CBS fields |  | 0.6 | 2026-04-26 | 2026-04-30 |  |  |  |  | Not Started | Delayed
17 | Phase-1 | Data Migration – Iteration 1 | Data Mapping | Mapping Definition | Define transformation logic |  | 0.6 | 2026-04-27 | 2026-05-01 |  |  |  |  | Not Started | Delayed
18 | Phase-1 | Data Migration – Iteration 1 | Data Cleansing | Data Quality | Remove duplicates |  | 0.6 | 2026-04-27 | 2026-05-01 |  |  |  |  | Not Started | Delayed
19 | Phase-1 | Data Migration – Iteration 1 | Data Cleansing | Data Quality | Correct inconsistencies |  | 0.5 | 2026-04-28 | 2026-05-02 |  |  |  |  | Not Started | Delayed
20 | Phase-1 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load customer data |  | 0.5 | 2026-05-03 | 2026-05-07 |  |  |  |  | Not Started | Delayed
21 | Phase-1 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load account data |  | 0.5 | 2026-05-03 | 2026-05-07 |  |  |  |  | Not Started | Delayed
22 | Phase-1 | Data Migration – Iteration 1 | Migration Execution | Trial Migration | Load Transaction data |  | 0.4 | 2026-05-08 | 2026-05-10 |  |  |  |  | Not Started | Delayed
23 | Phase-1 | Data Migration – Iteration 1 | Validation & Reconciliation | Data Validation | Migrated Data Validation* |  | 0.6 | 2026-05-03 | 2026-05-08 |  |  |  |  | Not Started | Delayed
24 | Phase-1 | Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Financial Report Validation* |  | 0.5 | 2026-05-04 | 2026-05-08 |  |  |  |  | Not Started | Delayed
25 | Phase-1 | Data Migration – Iteration 1 | Validation & Reconciliation | Financial Validation | Exception identification |  | 0.8 | 2026-05-09 | 2026-05-15 |  |  |  |  | Not Started | Delayed
26 | Phase-1 | Requirement Validation & Gap Analysis | Requirement Workshops | Core Modules | Core Module List* |  | 0.8 | 2026-05-09 | 2026-05-15 |  |  |  |  | Not Started | Delayed
27 | Phase-1 | Requirement Validation & Gap Analysis | Requirement Workshops | Digital Channels | Digital Channel Module List* |  | 0.5 | 2026-05-16 | 2026-05-20 |  |  |  |  | Not Started | Delayed
28 | Phase-1 | Requirement Validation & Gap Analysis | Integration Requirements | NPCI Rails | UPI IMPS NACH AEPS NFS BBPS FASTag |  | 0.5 | 2026-05-16 | 2026-05-20 |  |  |  |  | Not Started | Delayed
29 | Phase-1 | Requirement Validation & Gap Analysis | Integration Requirements | RBI Systems | NEFT RTGS |  | 0.6 | 2026-05-21 | 2026-05-25 |  |  |  |  | Not Started | Delayed
30 | Phase-1 | Requirement Validation & Gap Analysis | Integration Requirements | Government Systems | PFMS DBT CBDT |  | 0.6 | 2026-05-21 | 2026-05-25 |  |  |  |  | Not Started | Delayed
31 | Phase-1 | Requirement Validation & Gap Analysis | Integration Requirements | Switch & Channels | ATM POS UPI IMPS routing |  | 0.6 | 2026-05-22 | 2026-05-26 |  |  |  |  | Not Started | Delayed
32 | Phase-1 | Requirement Validation & Gap Analysis | Integration Requirements | Mandate | eNACH registration debit lifecycle |  | 0.5 | 2026-05-26 | 2026-05-30 |  |  |  |  | Not Started | On Track
33 | Phase-1 | Requirement Validation & Gap Analysis | Gap Analysis | Gap Identification | Identify gaps |  | 0.5 | 2026-05-26 | 2026-05-30 |  |  |  |  | Not Started | On Track
34 | Phase-1 | Requirement Validation & Gap Analysis | Gap Analysis | Gap Prioritization | Categorize gaps |  | 0.6 | 2026-05-27 | 2026-06-01 |  |  |  |  | Not Started | On Track
35 | Phase-1 | Requirement Validation & Gap Analysis | Sign-off | Approval | Requirement gap sign-off |  | 0.6 | 2026-05-27 | 2026-06-01 |  |  |  |  | Not Started | On Track
36 | Phase-1 | Solution Design & Configuration | Solution Design | Architecture Design | CBS architecture |  | 1 | 2026-05-11 | 2026-05-20 |  |  |  |  | Not Started | Delayed
37 | Phase-1 | Solution Design & Configuration | Solution Design | Architecture Design | Integration architecture (third party vendor) |  | 1 | 2026-05-11 | 2026-05-20 |  |  |  |  | Not Started | Delayed
38 | Phase-1 | Solution Design & Configuration | Product Configuration | Setup | Product Checklist* |  | 0.8 | 2026-05-21 | 2026-05-27 |  |  |  |  | Not Started | Delayed
39 | Phase-1 | Solution Design & Configuration | Accounting Setup | GL Product Setup | GL mapping interest charges* |  | 0.7 | 2026-05-21 | 2026-05-26 |  |  |  |  | Not Started | Delayed
40 | Phase-1 | Solution Design & Configuration | Integration Design | NPCI Design | API file structure sponsor bank |  | 0.8 | 2026-05-21 | 2026-05-28 |  |  |  |  | Not Started | Delayed
41 | Phase-1 | Solution Design & Configuration | Integration Design | RBI Design | NEFT RTGS design |  | 0.7 | 2026-05-22 | 2026-05-27 |  |  |  |  | Not Started | Delayed
42 | Phase-1 | Solution Design & Configuration | Integration Design | Switch Design | ATM POS UPI IMPS routing |  | 0.7 | 2026-05-22 | 2026-05-27 |  |  |  |  | Not Started | Delayed
43 | Phase-1 | Solution Design & Configuration | Integration Design | Government Design | PFMS DBT flows |  | 0.7 | 2026-05-23 | 2026-05-28 |  |  |  |  | Not Started | Delayed
44 | Phase-1 | Solution Design & Configuration | Settlement Design | Reconciliation | Settlement flows reconciliation |  | 0.7 | 2026-05-24 | 2026-05-29 |  |  |  |  | Not Started | On Track
45 | Phase-1 | Solution Design & Configuration | Mandate Design | Lifecycle | Registration execution cancellation |  | 0.6 | 2026-05-24 | 2026-05-28 |  |  |  |  | Not Started | Delayed
46 | Phase-1 | Development & Gap Closure | Core Development | Gap Development | Critical high gaps |  | 2 | 2026-05-29 | 2026-06-12 |  |  |  |  | Not Started | On Track
47 | Phase-1 | Development & Gap Closure | Integration Development | NPCI | UPI IMPS NACH AEPS |  | 1.5 | 2026-05-29 | 2026-06-10 |  |  |  |  | Not Started | On Track
48 | Phase-1 | Development & Gap Closure | Integration Development | RBI | NEFT RTGS |  | 1.2 | 2026-05-30 | 2026-06-08 |  |  |  |  | Not Started | On Track
49 | Phase-1 | Development & Gap Closure | Integration Development | Switch | ATM POS UPI IMPS |  | 1.2 | 2026-05-30 | 2026-06-08 |  |  |  |  | Not Started | On Track
50 | Phase-1 | Development & Gap Closure | Integration Development | Government | PFMS DBT CBDT |  | 1.2 | 2026-05-31 | 2026-06-10 |  |  |  |  | Not Started | On Track
51 | Phase-1 | Development & Gap Closure | Mandate Engine | Development | Registration validation execution |  | 1 | 2026-06-05 | 2026-06-12 |  |  |  |  | Not Started | On Track
52 | Phase-1 | Testing (QA + SIT) | Test Planning | Strategy | Test strategy test cases |  | 0.6 | 2026-06-10 | 2026-06-15 |  |  |  |  | Not Started | On Track
53 | Phase-1 | Testing (QA + SIT) | Functional Testing | CBS | Core Module + Functionalities List* |  | 1.5 | 2026-06-16 | 2026-06-28 |  |  |  |  | Not Started | On Track
54 | Phase-1 | Testing (QA + SIT) | Integration Testing | NPCI | UPI IMPS NACH |  | 1.2 | 2026-06-16 | 2026-06-26 |  |  |  |  | Not Started | On Track
55 | Phase-1 | Testing (QA + SIT) | Integration Testing | RBI | NEFT RTGS |  | 1 | 2026-06-17 | 2026-06-25 |  |  |  |  | Not Started | On Track
56 | Phase-1 | Testing (QA + SIT) | Integration Testing | Switch | ATM POS |  | 1 | 2026-06-17 | 2026-06-25 |  |  |  |  | Not Started | On Track
57 | Phase-1 | Testing (QA + SIT) | Integration Testing | Third Party Vendor | Third Party Vendor |  | 1 | 2026-06-17 | 2026-06-25 |  |  |  |  | Not Started | On Track
57 | Phase-1 | Testing (QA + SIT) | Settlement Testing | Validation | Settlement GL Transactions |  | 1 | 2026-06-18 | 2026-06-28 |  |  |  |  | Not Started | On Track
58 | Phase-1 | Testing (QA + SIT) | Failure Testing | Scenarios | Timeout reversal duplicate |  | 0.8 | 2026-06-19 | 2026-06-27 |  |  |  |  | Not Started | On Track
59 | Phase-1 | Training | Training Preparation | Material | Training materials SOP |  | 0.6 | 2026-06-20 | 2026-06-25 |  |  |  |  | Not Started | On Track
60 | Phase-1 | Training | Training Execution | Users | Branch operations |  | 0.6 | 2026-06-26 | 2026-07-01 |  |  |  |  | Not Started | On Track
61 | Phase-1 | Training | Training Execution | Technical | IT admin |  | 0.5 | 2026-06-26 | 2026-06-30 |  |  |  |  | Not Started | On Track
62 | Phase-1 | UAT- 1 (Bank Level) | UAT Planning | Scenarios | Define scope users |  | 0.6 | 2026-06-25 | 2026-06-30 |  |  |  |  | Not Started | On Track
63 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Core Banking | Core Module + Functionalities List* |  | 2.2 | 2026-07-01 | 2026-07-20 |  |  |  |  | Not Started | On Track
64 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Channels | Digital Channel Module List* |  | 2 | 2026-07-01 | 2026-07-18 |  |  |  |  | Not Started | On Track
65 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Payments | UPI IMPS NACH NEFT RTGS AEPS CTS |  | 2.2 | 2026-07-02 | 2026-07-22 |  |  |  |  | Not Started | On Track
66 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Government | PFMS DBT |  | 1.2 | 2026-07-03 | 2026-07-14 |  |  |  |  | Not Started | On Track
67 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Mandate | Registration execution |  | 1 | 2026-07-04 | 2026-07-13 |  |  |  |  | Not Started | On Track
68 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Settlement | GL reconciliation exception |  | 1 | 2026-07-05 | 2026-07-14 |  |  |  |  | Not Started | On Track
69 | Phase-1 | UAT- 1 (Bank Level) | UAT Execution | Reporting | Regulatory MIS* |  | 1 | 2026-07-06 | 2026-07-15 |  |  |  |  | Not Started | On Track
70 | Phase-1 | UAT- 1 (Bank Level) | Issue Resolution | Fixes | Resolve defects revalidation |  | 1.5 | 2026-07-21 | 2026-08-02 |  |  |  |  | Not Started | On Track
71 | Phase-1 | UAT- 1 (Bank Level) | Sign-off | Approval | Branch Ops Finance IT final |  | 0.6 | 2026-08-03 | 2026-08-07 |  |  |  |  | Not Started | On Track
72 | Phase-1 | Data Migration – Iteration 2 | Migration | Execution | Reload corrected data |  | 0.6 | 2026-08-08 | 2026-08-12 |  |  |  |  | Not Started | On Track
73 | Phase-1 | Data Migration – Iteration 2 | Validation | Final | Reconciliation |  | 0.6 | 2026-08-13 | 2026-08-17 |  |  |  |  | Not Started | On Track
74 | Phase-1 | UAT- 2 (High Level) | Execution | End to End | Full system validation |  | 1.5 | 2026-08-18 | 2026-08-30 |  |  |  |  | Not Started | On Track
75 | Phase-1 | UAT- 2 (High Level) | Reporting | Validation | MIS regulatory |  | 0.8 | 2026-08-22 | 2026-08-28 |  |  |  |  | Not Started | On Track
76 | Phase-1 | UAT- 2 (High Level) | Reporting | Validation | One Day Voucher Posting |  | 0.8 | 2026-08-22 | 2026-08-28 |  |  |  |  | Not Started | On Track
76 | Phase-1 | UAT- 2 (High Level) | Sign-off | Final | Business approval |  | 0.6 | 2026-08-31 | 2026-09-04 |  |  |  |  | Not Started | On Track
77 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Technical | Infra readiness |  | 0.6 | 2026-11-01 | 2026-11-03 |  |  |  |  | Not Started | On Track
78 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Data | Migration approval |  | 0.5 | 2026-11-01 | 2026-11-03 |  |  |  |  | Not Started | On Track
79 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Application | System validation |  | 0.6 | 2026-11-02 | 2026-11-04 |  |  |  |  | Not Started | On Track
80 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Integration | NPCI RBI Switch validation |  | 0.6 | 2026-11-02 | 2026-11-05 |  |  |  |  | Not Started | On Track
81 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Business | User readiness |  | 0.5 | 2026-11-03 | 2026-11-05 |  |  |  |  | Not Started | On Track
82 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Compliance | Regulatory validation |  | 0.5 | 2026-11-03 | 2026-11-06 |  |  |  |  | Not Started | On Track
83 | Phase-1 | Go-Live Readiness & Sign-Off | Sign-off | Final | Go-live approval |  | 0.6 | 2026-11-07 | 2026-11-10 |  |  |  |  | Not Started | On Track
84 | Phase-1 | Go-Live | Migration | Final | Production Data Restore |  | 0.2 | 2026-11-15 | 2026-11-15 |  |  |  |  | Not Started | On Track
85 | Phase-1 | Go-Live | Activation | CBS | Enable accounts transactions |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
86 | Phase-1 | Go-Live | Activation | NPCI | UPI IMPS NACH AEPS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
87 | Phase-1 | Go-Live | Activation | RBI | NEFT RTGS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
88 | Phase-1 | Go-Live | Activation | Switch | ATM POS UPI IMPS |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
89 | Phase-1 | Go-Live | Activation | Government | PFMS DBT |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
90 | Phase-1 | Go-Live | Activation | Channels | Mobile Internet APIs |  | 0.2 | 2026-11-16 | 2026-11-16 |  |  |  |  | Not Started | On Track
91 | Phase-1 | Go-Live | Monitoring | Transactions | Validate transactions |  | 0.6 | 2026-11-16 | 2026-11-18 |  |  |  |  | Not Started | On Track
92 | Phase-1 | Go-Live | Support | Issue Handling | Resolve issues |  | 0.8 | 2026-11-16 | 2026-11-20 |  |  |  |  | Not Started | On Track
93 | Phase-1 | Post Go-Live Stabilization | Hypercare | Support | Onsite support |  | 1.5 | 2026-11-17 | 2026-11-28 |  |  |  |  | Not Started | On Track
94 | Phase-1 | Post Go-Live Stabilization | Monitoring | Performance | System monitoring |  | 1.2 | 2026-11-17 | 2026-11-26 |  |  |  |  | Not Started | On Track
95 | Phase-1 | Post Go-Live Stabilization | Resolution | Fixes | Bug fixing |  | 1.2 | 2026-11-18 | 2026-11-28 |  |  |  |  | Not Started | On Track
96 | Phase-1 | Post Go-Live Stabilization | Closure | Documentation | Closure lessons learned |  | 0.6 | 2026-11-25 | 2026-11-30 |  |  |  |  | Not Started | On Track
Formulas:
Project Start Date = [Project Start Date, row below]

## Sheet1
Font | Cambria
| Chart/Graph | Requirement
| Task wise Bar chart | Planned vs Achieved
| Task wise Doughnut chart | Doughnut Graft with Percentage
| Phase Wise Bar Chart | Planned vs Achieved
| Phase wise Doughnut chart | Doughnut Graft with Percentage
| Overall Bar chart | Planned vs Achieved
| Overall Doughnut chart | Doughnut Graft with Percentage